Meeting 01 – Tuesday 20 October

People Present:
- Connor
- Jordan
- Joseph
- Ryan

Progress from Last Meeting
- Large list of various local Rock/Metal bands in Worthing and Brighton
- Event hire research shows that Sticky Mikes and Green Door Store cost around 150 pounds
- Decided on Venue – 42

Tasks
- Book Venue – Connor
- Decide on possible artists to play – all
- Enquire about artist booking prices/book artists – Joe

Meeting 02 – Wednesday 21 October

People Present
- Connor
- Jordan
- Joseph
- Ryan

Progress from Last Meeting
Decided on Venue/Date of gig (01 Dec @ Bar 42, Worthing)

Tasks
- Enquire and book bands – Joe
- Sort out stage times - All
- Create posters - Connor
- Adverstise and promotion – All

Meeting 03 - Wednesday 28th October

People Present
- Connor
- Jordan
- Joseph
- Ryan

Progress from Last Meeting
- Organised the gig timetable
- Booked two bands for £40 each
- Decided on a £3 charge on the door
- Allocated roles for the event to each member

Tasks
- Book third band (if Vile decides against playing)
- Create sales pitch and posters - Connor
- begin adverstising - all

Meeting 04 - Wednesday 09th December

People Present
- Connor
- Jordan
- Joseph
- Ryan

Progress from Last Meeting
- Promoted our event using facebook page
- Handed out flyers and put up posters

Tasks
- Check that all the bands have all the information and are ok with Tuesday
- Obtain a float for cash box

Meeting 05 – Monday 14th December

People Present
- Connor
- Jordan
- Joseph
- Ryan

Progress from Last Meeting
Obtained Float for cash box

Tasks
Sort out amplifier for Vile Discectomy

Meeting 06 – Tuesday 15th December

People Present
- Connor
- Jordan
- Joseph
- Ryan

Progress from Last Meeting
Booked an amplifier for Vile Discectomy to use

Tasks
Gig

Meeting 07 – Wednesday 16th December

People Present
- Connor
- Jordan
- Joseph
- Ryan
- Phill Minns

Progress from Last Meeting
Had the Event

Tasks
Record interview evaluation of our event